## Class web Charter
Project Charter
General Project Information
Project Name	Design and Development of Class Website
Project Sponsor	Department of Computer Science
Project Manager	Gitesh Shewale
Start Date	1 jan 2026
Project End Date	1 june 2026
Describe the Project , Purpose of Project and Objectives
Project Description	The class website is designed to provide a centralized online platform for students and teachers. It will help in sharing academic information such as syllabus, notices, study materials, and allow secure login access for students and teachers.
Purpose of Project	The purpose of this project is to design and develop a user-friendly and secure class website that improves communication and academic management.
Project Objectives	To develop a responsive class website. / To provide secure student and teacher login portals / To display syllabus and academic resources / To manage notices and announcements efficiently
Approch:	The project follows a phased approach starting with requirement analysis and planning. This is followed by design, development, and testing of the class website.
Define the Project Scope and Schedule
Within Scope	Home page Syllabus page Student login portal Teacher login portal Notice board Contact page
Outside of Scope	Online payment system Mobile application
Tentative Schedule	Key Milestone	Start	Complete
	Project initiation and requirement analysis	1 jan 2026	5 feb 2026
	Website design and development	6 march 2026	20 apr 2026
	Testing, deployment, and final submission	21 may 2026	1 june 2026
Budget Information:
The project uses open-source tools, so no major development cost is involved.
Expenses are limited to internet usage and basic hosting, if required.
The total project budget is minimal and managed within academic constraints.
Role and Responsibilities:
Name	Roles	Responsbilities
Instructor	Project Sponsor & Content Owner	Approved and funding
Students	End Users	Provide feedback
Project Manager	Planning & Execution	planning and control
Web Developer	Design & Development	system development
Tester	Testing & Validation	quality assurance
Project Sign Off:
Name	Signature	Date
Project Manager
Web Developer

## e-commerce Charter
Project Charter
General Project Information
Project Name	Design and Development of an E-Commerce Website
Project Sponsor	Department of Computer Science
Project Manager	Pratik Mahale
Start Date	1 Dec 2025
Project End Date	1 Jan 2026
Describe the Project , Purpose of Project and Objectives
Project Description	With the rapid growth of online shopping, an e-commerce website provides businesses with a digital platform to sell products efficiently. This project focuses on designing and developing a secure and user-friendly e-commerce website that allows users to browse products, manage carts, place orders, and maintain user accounts.
Purpose of Project	To design an attractive and responsive e-commerce website / To implement a product catalog with detailed listings. To provide shopping cart and order management features / To develop secure user registration and login / To ensure smooth checkout and order tracking
Project Objectives	To design an attractive and responsive e-commerce website To implement a product catalog with detailed listings To provide shopping cart and order management features To develop secure user registration and login To ensure smooth checkout and order tracking
Approch:	The project follows a phased approach starting with requirement analysis and planning.This is followed by design, development, and testing of the E-commerce website.
Define the Project Scope and Schedule
Within Scope	Home page Product catalog User registration and login Shopping cart Order management system User account management Contact and support
Outside of Scope	Mobile application Third-party logistics integration Advanced analytics and AI recommendations
Tentative Schedule	Key Milestone	Start	Complete
	Requirement analysis and planning	1 Dec 2025	5 Jan 2025
	Website design and development	6 Dec 2025	20 Dec 2025
	Testing, deployment, and final submission	21 Dec 2025	1 Jan 2026
Budget Information:
The project uses open-source technologies, so development cost is minimal. / Expenses are limited to internet usage and optional hosting charges. / Overall budget is low and suitable for an academic project.

Role and Responsibilities:
Name	Roles	Responsbilities
Project Manager	Planning & Execution	planning and control
Web Developer	Design & Development	system development
Tester	Testing & Validation	quality assurance
Project Sign Off:
Name	Signature	Date
Project Manager
Web Developer

	E-Commerce Website Project Plan (Chart)
	Section	Details
	Overview	Develop a user-friendly e-commerce website for browsing products, cart, and orders.
	Project Organization	Project Manager (Pratik Mahale), Web Developer, Tester
	Managerial Process Plan	Phases: Planning → Design → Development → Testing → Deployment
	Technical Process Plans	Tech: HTML, CSS, JS, PHP/Node.js, MySQL. Features: Login, catalog, cart, orders
	Supporting Process Plans	Testing, documentation, Git version control, maintenance
	Scope	Includes: catalog, login, cart, orders. Excludes: mobile app, AI features
	Schedule	1 Dec 2025 – 1 Jan 2026
	Budget	Low cost (open-source tools)