## Sheet1
Project Charter: Library Management System
General Project Information
Field		Details
Project Name		Library Management System
Project Sponsor		Department of Computer Science
Project Manager		Pratik Mahale
Start Date		1 Dec 2025
End Date		1 Jan 2026

Project Description, Purpose & Objectives
Section		Details
Description		A system to manage library operations like book records, issuing, returning, and user management in a simple and efficient way.
Purpose		To digitize library work, reduce manual effort, and improve record management.
Objectives		Book management, user login, issue/return system, search books, maintain records

Approach
Phased approach: Requirement Analysis → Design → Development → Testing

Scope & Schedule
Within Scope		Book records, user login, issue/return, search system
Outside Scope		Mobile app, AI recommendations, external integrations
Milestone	Start		End
Planning	1 Dec 2025		5 Dec 2025
Development	6 Dec 2025		20 Dec 2025
Testing & Deployment	21 Dec 2025		1 Jan 2026

Budget
Low cost (open-source tools, minimal expenses)

Roles & Responsibilities
Role		Responsibility
Project Manager		Planning & control
Developer		System development
Tester		Testing & quality check
Project Sign Off:
Name	Signature	Date
Project Manager
Web Developer

	Library Management System Project Plan (Chart)
	Section	Details
	Overview	System to manage books, users, and issue/return process.
	Project Organization	Project Manager, Developer, Tester
	Managerial Process Plan	Planning → Design → Development → Testing → Deployment
	Technical Process Plans	HTML, CSS, JS, PHP/Node.js, MySQL; features: login, books, issue/return
	Supporting Process Plans	Testing, documentation, Git, maintenance
	Scope	Includes: books, login, issue/return; Excludes: mobile app, AI
	Schedule	1 Dec 2025 – 1 Jan 2026
	Budget	Low cost