## Sheet1
Project Charter: Restaurant Management System
General Project Information
Field				Details
Project Name				Restaurant Management System
Project Sponsor				Department of Computer Science
Project Manager				Pratik Mahale
Start Date				1 Dec 2025
End Date				1 Jan 2026

Project Description, Purpose & Objectives
Section				Details
Description				A system to manage restaurant operations like menu, orders, billing, and customer records efficiently.
Purpose				To automate restaurant processes and improve service efficiency.
Objectives				Menu management, order processing, billing system, user login, record maintenance

Approach
Phases: Requirement Analysis → Design → Development → Testing

Scope & Schedule
Within Scope				Menu management, order system, billing, user login
Outside Scope				Mobile app, online delivery integration, AI features
Milestone		Start			End
Planning		1 Dec 2025			5 Dec 2025
Development		6 Dec 2025			20 Dec 2025
Testing & Deployment		21 Dec 2025			1 Jan 2026

Budget
Low cost (open-source tools)

Roles & Responsibilities
Role				Responsibility
Project Manager				Planning & control
Developer				System development
Tester				Testing & quality check

Project Sign-Off
Name	Role		Signature			Date
Pratik Mahale	Project Manager		____________			________
Web Developer	Developer		____________			________
Tester	Tester		____________			________

	Restaurant Management System Project Plan (Chart)
	Section	Details
	Overview	System to manage menu, orders, billing, and customers.
	Project Organization	Project Manager, Developer, Tester
	Managerial Process Plan	Planning → Design → Development → Testing → Deployment
	Technical Process Plans	HTML, CSS, JS, PHP/Node.js, MySQL; features: menu, orders, billing
	Supporting Process Plans	Testing, documentation, Git, maintenance
	Scope	Includes: menu, orders, billing; Excludes: mobile app, AI
	Schedule	1 Dec 2025 – 1 Jan 2026
	Budget	Low cost