## Sheet1
Project Charter: College ERP System
General Project Information
Field				Details
Project Name				College ERP System
Project Sponsor				Department of Computer Science
Project Manager				Pratik Mahale
Start Date				1 Feb 2026
End Date				1 Aug 2026

Project Description, Purpose & Objectives
Section				Details
Description				A centralized system to manage student records, faculty data, attendance, exams, fees, and administrative operations efficiently.
Purpose				To automate college operations and improve data management, transparency, and efficiency.
Objectives				Student management, faculty management, attendance tracking, exam/result system, fee management, user login, report generation

Approach
Phases:
Requirement Analysis → System Design → Development → Testing → Deployment

Scope & Schedule
Scope
Category				Details
Within Scope				Student records, faculty management, attendance system, exam & result module, fee management, user login
Outside Scope				Mobile application, AI-based analytics, online learning integration

Milestones
Milestone		Start			End
Planning		1 Feb 2026			10 Feb 2026
Design		11 Feb 2026			25 Feb 2026
Development		26 Feb 2026			31 May 2026
Testing		1 Jun 2026			30 Jun 2026
Deployment		1 Jul 2026			10 Jul 2026
Maintenance		11 Jul 2026			1 Aug 2026

Budget
Category				Details
Budget Type				Medium Cost
Estimated Cost				₹15,00,000 – ₹18,00,000
Tools				Open-source + Licensed tools

Roles & Responsibilities
Role				Responsibility
Project Manager				Planning, scheduling, monitoring
Developers				System development & coding
Tester				Testing & quality assurance
Database Administrator				Database management
UI Designer				Interface design

Project Sign-Off
Name	Role		Signature			Date
Pratik Mahale	Project Manager		____________			________
Developer	Developer		____________			________
Tester	Tester		____________			________

📊 College ERP System Project Plan (Chart)
Section				Details
Overview				System to manage students, faculty, attendance, exams, fees, and administration
Project Organization				Project Manager, Developers, Tester, DBA, UI Designer
Managerial Process Plan				Planning → Design → Development → Testing → Deployment
Technical Process Plans				HTML, CSS, JavaScript, PHP/Node.js, MySQL; modules: student, faculty, attendance, exams, fees
Supporting Process Plans				Testing, documentation, version control (Git), maintenance
Scope				Includes: student, faculty, attendance, exam, fees; Excludes: mobile app, AI
Schedule				1 Feb 2026 – 1 Aug 2026
Budget				Medium cost

Project Charter: Pune Metro Rail Project
General Project Information
Field				Details
Project Name				Pune Metro Rail Project
Project Sponsor				Maharashtra Metro Rail Corporation Limited
Project Manager				Project Director (Maha Metro)
Start Date				24 Dec 2016
End Date				31 Dec 2026 (estimated full completion)

Project Description, Purpose & Objectives
Section				Details
Description				A rapid transit system designed to provide efficient, safe, and eco-friendly transportation across Pune.
Purpose				To reduce traffic congestion, pollution, and travel time while improving urban mobility.
Objectives				Develop metro corridors, improve connectivity, reduce road traffic, ensure sustainable transport, enhance passenger experience

Approach
Phases:
Feasibility Study → Planning → Design → Construction → Testing → Commissioning → Operations

Scope & Schedule
Scope
Category				Details
Within Scope				Metro rail corridors, stations, signaling systems, ticketing system, passenger facilities
Outside Scope				Intercity rail expansion, private transport systems, unrelated urban infrastructure

Milestones
Milestone		Start			End
Planning & Approval		2014			2016
Construction Phase 1		2017			2022
Partial Operations		2022			2023
Phase 2 Construction		2023			2026
Full Completion		—			31 Dec 2026

Budget
Category				Details
Budget Type				High Cost Infrastructure Project
Estimated Cost				₹11,000+ Crores
Funding Sources				Government of India, Government of Maharashtra, Loans, PPP

Roles & Responsibilities
Role				Responsibility
Project Director				Overall project execution
Engineers				Design & construction
Contractors				Civil work execution
Government Authorities				Approvals & funding
Safety Officers				Ensure safety compliance

Project Sign-Off
Name	Role		Signature			Date
Project Director	Project Head		____________			________
Government Authority	Sponsor		____________			________
Chief Engineer	Technical Head		____________			________

📊 Pune Metro Rail Project Plan (Chart)
Section				Details
Overview				Metro rail system for urban transport in Pune
Project Organization				Project Director, Engineers, Contractors, Government
Managerial Process Plan				Planning → Design → Construction → Testing → Operation
Technical Process Plans				Civil engineering, rail systems, signaling, electrification
Supporting Process Plans				Safety management, quality control, documentation, maintenance
Scope				Includes: metro lines, stations, ticketing; Excludes: non-metro transport systems
Schedule				2016 – 2026
Budget				Very high cost

Project Charter: Banking System
General Project Information
Field				Details
Project Name				Banking System
Project Sponsor				Banking Institution / Finance Department
Project Manager				Pratik Mahale
Start Date				1 March 2026
End Date				1 September 2026

Project Description, Purpose & Objectives
Section				Details
Description				A software system designed to manage banking operations such as account management, transactions, loans, and customer records securely.
Purpose				To automate banking processes, improve transaction efficiency, and ensure secure financial operations.
Objectives				Account management, deposit/withdrawal, fund transfer, loan management, user authentication, transaction history

Approach
Phases:
Requirement Analysis → System Design → Development → Testing → Deployment

Scope & Schedule
Scope
Category				Details
Within Scope				Account creation, transactions, fund transfer, loan system, user login, reports
Outside Scope				Cryptocurrency integration, advanced AI fraud detection, mobile banking app

Milestones
Milestone		Start			End
Planning		1 Mar 2026			10 Mar 2026
Design		11 Mar 2026			25 Mar 2026
Development		26 Mar 2026			30 Jun 2026
Testing		1 Jul 2026			31 Jul 2026
Deployment		1 Aug 2026			15 Aug 2026
Maintenance		16 Aug 2026			1 Sep 2026

Budget
Category				Details
Budget Type				Medium to High Cost
Estimated Cost				₹20,00,000 – ₹25,00,000
Tools				Secure frameworks, database systems

Roles & Responsibilities
Role				Responsibility
Project Manager				Planning, monitoring, control
Developers				Backend & frontend development
Tester				System & security testing
Database Administrator				Data management & security
Security Analyst				Security implementation

Project Sign-Off
Name	Role		Signature			Date
Pratik Mahale	Project Manager		____________			________
Developer	Developer		____________			________
Tester	Tester		____________			________

📊 Banking System Project Plan (Chart)
Section				Details
Overview				System to manage accounts, transactions, loans, and customer data
Project Organization				Project Manager, Developers, Tester, DBA, Security Analyst
Managerial Process Plan				Planning → Design → Development → Testing → Deployment
Technical Process Plans				Java/Python, HTML, CSS, JavaScript, MySQL/Oracle; modules: accounts, transactions, loans
Supporting Process Plans				Testing, security audits, documentation, version control (Git), maintenance
Scope				Includes: accounts, transactions, loans; Excludes: crypto, AI systems
Schedule				1 Mar 2026 – 1 Sep 2026
Budget				Medium to High cost

Project Charter: Solar Power Plant System
General Project Information
Field				Details
Project Name				Solar Power Plant System
Project Sponsor				Renewable Energy Department / Government Authority
Project Manager				Pratik Mahale
Start Date				1 April 2026
End Date				1 December 2026

Project Description, Purpose & Objectives
Section				Details
Description				A system designed to generate electricity using solar energy through photovoltaic panels and manage power distribution efficiently.
Purpose				To promote renewable energy usage and reduce dependency on non-renewable energy sources.
Objectives				Solar power generation, energy storage management, grid integration, monitoring system, efficiency optimization

Approach
Phases:
Feasibility Study → Planning → Design → Installation → Testing → Commissioning → Maintenance

Scope & Schedule
Scope
Category				Details
Within Scope				Solar panel installation, inverter setup, battery storage, monitoring system, grid connection
Outside Scope				Wind energy integration, hydro power systems, advanced AI forecasting

Milestones
Milestone		Start			End
Feasibility Study		1 Apr 2026			15 Apr 2026
Planning		16 Apr 2026			30 Apr 2026
Design		1 May 2026			31 May 2026
Installation		1 Jun 2026			30 Sep 2026
Testing		1 Oct 2026			31 Oct 2026
Commissioning		1 Nov 2026			15 Nov 2026
Maintenance		16 Nov 2026			1 Dec 2026

Budget
Category				Details
Budget Type				High Cost Infrastructure
Estimated Cost				₹50,00,000 – ₹2,00,00,000 (depending on plant size)
Tools				Solar panels, inverters, monitoring systems

Roles & Responsibilities
Role				Responsibility
Project Manager				Overall planning & execution
Electrical Engineers				System design & installation
Technicians				Panel installation
Quality Engineers				Testing & inspection
Maintenance Team				Post-installation support

Project Sign-Off
Name	Role		Signature			Date
Pratik Mahale	Project Manager		____________			________
Engineer	Technical Head		____________			________
QA Engineer	Tester		____________			________

📊 Solar Power Plant System Project Plan (Chart)
Section				Details
Overview				System to generate and manage electricity using solar energy
Project Organization				Project Manager, Engineers, Technicians, QA Team
Managerial Process Plan				Feasibility → Planning → Design → Installation → Testing → Commissioning
Technical Process Plans				Solar panels, inverters, batteries, grid integration systems
Supporting Process Plans				Safety checks, testing, documentation, maintenance
Scope				Includes: solar generation, storage, monitoring; Excludes: wind/hydro systems
Schedule				1 Apr 2026 – 1 Dec 2026
Budget				High cost

s