## class web RTM
Project name: class website Manager: Gitesh Shewale		Requirements Traceability Matrix

Requirement no	Name	Category	Priority	Source	Status
R01	Laptop	Hardware	High	Project charter and corporate laptop specifications	Complete. Laptops procured meet requirement with minimum 8GB RAM and SSD storage.
R02	Server Hardware	Hardware	High	Hosting provider specifications	Complete. Server resources meet required CPU, memory, and storage specifications.
R03	Network Connectivity	Hardware	High	Institutional IT standards	Complete. Reliable internet connection with sufficient bandwidth provided.
R04	Home Page Display	Functional	High	Project charter and faculty requirements	Complete. Homepage developed with class details, navigation menu, and announcements section.
R05	Student Information page	Functional	High	Student requirements documents	Complete. Student details page implemented with secure access.
R06	Faculty information page	Functional	Medium	Faculty requirements	Complete. Faculty profile page added with contact details.
R07	Course material upload	Functional	High	Faculty and admin requirements	Complete. Admin can upload and manage study materials successfully.
R08	Contact form	Functional	Low	Student feedback	Complete. Contact form sends queries to admin email.
R09	Admin login	Security	High	Corporate website standards	Complete. Secure authentication implemented for admin users.
R10	Responsive design	Non-Functional	High	Corporate web standards	Complete. Website is responsive across desktop, tablet, and mobile devices.

Scope statement

Project name: Class website
Date: Jan 1	Prepared By:Gitesh Shewale

Project Summary and Justification: The Class Website Project aims to develop a web based platform for students, teachers and administrators to manage academic information efficiently. It will provide student and teacher profile, class schedules, announcements, and course materials. The website will be responsive and include an admin panel for content management, streaming communication and reducing manual record-keeping.
Product-related deliverables: 1.Class Website: Fully functional, responsive, and secure. / 2.Templates and Resources: Lecture notes, PDFs, presentations, and example documents. / 3.Student & Faculty Profiles: Complete and up-to-date information. / 4.Announcements and Timetable: Sections for notices, events, and schedules. / 5.Admin Panel: For content management and user access control. / 6.Search and Contact Features: Search by keywords and submit queries. / 7.Test Plan: Documenting testing procedures, responsibilities, and bug reporting. / 8.User Instructions & Documentation: Guides for using the website.
Project Success Criteria: / 1.The website is completed on time and within budget. / 2.The system is fully functional, secure, and accessible on desktop, tablet, and mobile. / 3.Students and faculty can easily access class information, resources, and schedules. / 4.Announcements, timetables, and course materials are accurately maintained and updated. / 5.The website reduces manual communication and improves class organization. / 6.Positive user adoption and feedback from students and faculty.
Scope Characteristics: / Clearly defined – Only class-related features are included / Limited – No extra features like online exams or payments / Measurable – Pages and features can be verified / Controlled – Changes need approval / Achievable – Can be completed in limited time

Scope Specifications: / Project Objective – To develop a class website / Deliverables – Website, source code, documentation / Functional Features / Home page / Class information / Timetable / Notices and announcements / Assignment section / Contact details / Constraints – Limited time and resources / Assumptions – Internet access is available

Functional Requirements / (What the website should do) / Display class information / Show timetable / Publish notices and announcements / Upload and download assignments / Provide subject and syllabus details / Contact information display / Admin can update content

## E-commerce RTM
Project name: E- commerce Project manager:Pratik Mahale		Requirements Traceability Matrix

Requirement No.	Name	Category	Priority	Source	Status
R1	User registration	Functional	High	Client requirements	Complete. Users can register with email and password.
R2	User login	Security	High	Client requirements	Complete. Secure login implemented.
R3	Product catalog	Functional	High	Business requirements	Complete. Products displayed by category.
R4	Product search	Functional	Medium	User requirements	Complete. Keyword-based search enabled.
R5	Shopping cart	Functional	High	Client requirements	Complete. Users can add and remove items.
R6	Online payment	Functional	High	Business requirements	Complete. Payment gateway integrated.
R7	Order management	Functional	High	Admin requirements	Complete. Orders tracked and updated.
R8	Admin panel	Functional	Medium	Project charter	Complete. Admin can manage products and orders.
R9	Website security	Non-Functional	High	Corporate standards	Complete. HTTPS and data encryption used.
R10	Server hardware	Hardware	High	Hosting provider specifications	Complete. Server meets CPU, RAM, and storage requirements.

Scope statement

Project name: E- commerce website
Date: Jan 1	Prepared By:Pratik Mahale

Project Summary and Justification: The project will develop a secure, user-friendly e-commerce website to allow customers to browse, order, and pay online. It will improve customer experience, increase sales, and reduce manual order processing while providing analytics for business optimization.
Product-related deliverables: / 1. Fully functional e-commerce website with product catalog, shopping cart, and checkout. / 2.Admin panel for managing products, orders, and customers. / 3.Customer accounts with order history and profile management. / 4.Integration with payment gateway and notifications system. / 5.Test plan documenting testing procedures, responsibilities, and bug reporting. / 6.User documentation and guides for customers and admin.
Project Success Criteria: / 1.Completed on time and within budget. / 2.Website is secure, responsive, and fully functional. / 3.Customers can easily browse, order, and pay for products online. / 4.Admin can manage products, orders, and users effectively. / 5.Positive customer feedback and smooth business operations. / 6.Website helps increase sales and reduce manual order processing.
Key Scope Characteristics: / Clearly defined – Scope should be clear and understandable / Measurable – Work can be measured and verified / Limited – Only defined work is included / Controlled – Changes are managed properly / Realistic – Achievable within time and cost

Scope Specifications Include: / Project objectives / Deliverables / Functional features / Constraints / Assumptions / Acceptance criteria

Functional Requirements / (What the system should do) / User registration and login / Product search and view / Shopping cart / Online payment processing / Order placement and tracking / Admin product management / Customer support