## Sheet1
Project name: Restaurant Management System
Manager: Pratik Mahale

Requirements Traceability Matrix (RTM)
Requirement No	Name	Category	Priority	Source	Status
R01	Computer Systems	Hardware	High	Project charter and restaurant IT standards	Complete. Computer systems installed at billing and kitchen counters meet minimum specifications.
R02	Server / Cloud Hosting	Hardware	High	Hosting provider specifications	Complete. Server resources meet required CPU, memory, and storage needs.
R03	Network Connectivity	Hardware	High	Institutional IT standards	Complete. Reliable internet connection with sufficient bandwidth provided.
R04	Home Page Display	Functional	High	Project charter and restaurant requirements	Complete. Homepage developed with restaurant details, menu highlights, and offers.
R05	Menu Management	Functional	High	Manager requirements	Complete. Admin can add, update, and remove food items with prices.
R06	Order Management	Functional	High	Staff requirements	Complete. System supports placing, updating, and tracking customer orders.
R07	Billing & Payment	Functional	High	Management requirements	Complete. Billing system generates bills and supports cash and digital payments.
R08	Table Reservation	Functional	Medium	Customer feedback	Complete. Customers can reserve tables online.
R09	Admin Login	Security	High	Corporate security standards	Complete. Secure authentication implemented for admin and staff users.
R10	Responsive Design	Non-Functional	High	Corporate web standards	Complete. System works smoothly on desktop, tablet, and mobile devices.

Scope Statement
Project name: Restaurant Management System
Date: Jan 1
Prepared By: Pratik Mahale
Project Summary and Justification
The Restaurant Management System Project aims to develop a web-based system to manage restaurant operations efficiently. It helps manage menus, customer orders, billing, payments, and table reservations. The system reduces manual work, minimizes errors, improves service speed, and enhances customer satisfaction. The application is responsive and includes an admin panel for complete control.
Product-related Deliverables
Restaurant Management Website: Fully functional, responsive, and secure system.
Menu Management Module: Add, edit, and delete food items with pricing.
Order Management System: Manage dine-in and takeaway orders.
Billing & Payment Module: Automated bill generation and payment tracking.
Table Reservation System: Online reservation and table availability tracking.
Admin Panel: Manage menu, staff access, orders, and reports.
Search & Filter Features: Easy food item and order search.
User Instructions & Documentation: Guides for staff and admin users.
Project Success Criteria
The system is completed on time and within budget.
The system is secure, reliable, and accessible on desktop, tablet, and mobile devices.
Restaurant staff can manage orders and billing efficiently.
Customers receive faster service and accurate bills.
The system reduces manual paperwork and order errors.
Positive feedback from restaurant management, staff, and customers.