## Sheet1
	Class-website

Activity / Phase	Project Manager	Business Analyst	System Designer	Developer	Quality Assurance	System Administrator
Project Initiation	A	C	I	I	I	I
Feasibility Study	A	R	C	I	I	I
Project Proposal	A	R	C	I	I	I
Project Charter	A	R	C	I	I	I
Requirement Gathering	C	R	I	I	I	I
SRS Preparation	C	R	C	I	I	I
Requirement Validation	A	R	C	I	I	I
High-Level Design	C	C	R	I	I	I		R=Responsible A = Accountable C = Consulted I = Informed
Database Design	I	C	R	C	I	I
UI Design	I	C	R	C	I	I
Logic & Authentication	I	I	C	R	I	I
Menu Management	I	I	C	R	I	I
Order Management	I	I	C	R	I	I
Table Reservation	I	I	C	R	I	I
Unit Testing	I	I	I	C	R	I
Integration Testing	I	I	I	C	R	I
System Testing	I	I	I	C	R	I
Deployment	A	I	I	C	I	R
Server Setup	I	I	I	I	I	R
Project run	A	I	I	I	I	R