## Sheet1
	E-com RACI chart

Activity / Milestone	Project Manager	Business Analyst	System Designer	Developer	Quality Assurance	System Administrator
Requirement Analysis	A	R	C	I	I	I
Requirements Approved (Milestone)	A	R	I	I	I	I
System & Database Design	C	C	R	I	I	I
Design Approved (Milestone)	A	I	R	I	I	I
Home Page Development	I	I	C	R	I	I			R=Responsible A = Accountable C = Consulted I = Informed
Product Catalog Module	I	I	C	R	I	I
Shopping Cart & Checkout	I	I	C	R	I	I
User Account & Order Management	I	I	C	R	I	I
Payment Gateway Integration	I	I	C	R	I	C
Core Development Completed (Milestone)	A	I	I	R	I	I
Testing	I	I	I	C	R	I
Testing Completed (Milestone)	A	I	I	I	R	I
Deployment	A	I	I	C	I	R
Website Live (Milestone)	A	I	I	I	I	R